## Time schedule
Time schedule Circular PP | 2017-041810-4 | 2018-01-19
Reportering periodes (indication of 6 month intervals) |  | 1. reportering periode | [6 empty] | 2. reportering periode | [5 empty] | 3. reportering periode | [5 empty] | 4. reportering periode | [5 empty] | 5. reportering periode | [5 empty] | 6. reportering periode
|  | sep. 17 | okt. 17 | nov. 17 | dec. 17 | jan. 18 | feb. 18 | mar. 18 | apr. 18 | may 18 | jun. 18 | jul. 18 | aug. 18 | sep. 18 | okt. 18 | nov. 18 | dec. 18 | jan. 19 | feb. 19 | mar. 19 | apr. 19 | may 19 | jun. 19 | jul. 19 | aug. 19 | sep. 19 | okt. 19 | nov. 19 | dec. 19 | jan. 20 | feb. 20 | mar. 20 | apr. 20 | may 20 | jun. 20 | jul. 20 | aug. 20 | sep. 20
WP1 Project management and administration
Support Project Coordination | Support the City of Aalborg in coordinating the Circular PP project: Attend and support facilitating the project meetings; Provide support to the agenda for steering Committee and project meetings; Providing guidance on submitting technical reports
Provide support in developing a project handbook
Assist in preparing the biannual report
Provide general support for project management team in City of Aalborg
Provide advice on developing and implementing specific tasks ind the project
Partner Meetings | Participate in the partner meetings
WP1 Technical support
Support the implementation and content development of the project | Provide advice on developing and implementing the overall work programme
provide and advice to the partners on state aids relevant issues
Support the implementation of specific tasks which are to be defined. Example tasks include providing technical support for implementation of circular procurement to the local government partners of the project, support the training and mentoring programme of the Circular PP project
WP2.3 Organiosational structure of public bodies relevant to public
Publication of a peer reviewed article | Assist in the development of a published peer reviewed article
WP5.1 Communication stretegy
Communication strategy | Assist in preparing and updating of the project’s communication strategy
Assist in promoting synergies and coordination with other funing sources for implementation of practical results from CPP
Help reach target groups
Assist in assuring a good and constant flow of communication between the partners
Dissemination of outcomes | Assist in disseminating the outcomes of the project across Europe through procurement focussed websites, newsletter, forums, social media etc
Promote the activities of the project 10 times per year through the channels above
Assist in the preparation of 2 opinion articles about the circular procurement pilots the local government partners undertake
Project Newsletters | Responsible for biannual newsletters
Update project website with content | Assist in update project website
Video | Prepare interview guide for video interviews
Infographics (design costs 2000 per graphic) | Assist in creating infographics to outline what the project is trying to achieve graphically
Opinion articles about the pilots /press releases (2 each) | Assist in preparation of 2 articles about pilots in cooperation with project management team and project partners
WP5.2 Events
Promoting the project at key events | Assist in the preparation of material and present at one event
WP5.3 Congress
Host and coordinate the final project event at circular procurement congress/ EcoProcura/ Procura+ Seminar | Assist in preparing, implementing and participating the final project event at a Circular Procurement Congress